## Sheet1
TestLog
What being used | How | Test data used |  | Expected Results |  | Date | Actual Results | Action Taken
1.Validation of input | Enter typical ,boundary | Input String: |  |  |  | 16/03/2017
edit profile for students | values and value should | Information "myhomeat.." |  | Input data successful |  |  | Worked as expected results | None
| be rejected | Email "huydd@gmail.com
ChangePasswordTo 12345
|  | Information "empty" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
|  | Email "huyddgmail.com" |  | Error message: Need signal @ in email adress
|  | ChangePassword "empty" |  | Error message: Need to fill out this field
|  | Information "blank" |  | Error message: Need to fill out this fied |  |  | Still running | Need to validate
|  | Email "blank" |  | Error message: Need to fill out this fied |  |  | Worked
|  | ChangePassword "blank" |  | Error message: Need to fill out this fied |  |  | Still running | Need to validate
2. Validation of input in login | Input username and | Input |  |  |  | 16/03/2017
of Student | password | UserName: tudmgc00376 |  | Login in system if username is true |  |  | Worked as expected results | None
|  | Password: 12345 |  | Error message: Invalid username or password
Input
|  | UserName: hungnt00000 |  | Invalid Username if username is not true |  |  | Worked as expected results | None
|  | Password: 12345 |  | Error message: Invalid username or password
Input
|  | UserName: lampt00512 |  | Invalid Password if password is not true |  |  | Worked as expected results | None
|  | Password: 1234 |  | Error message: Invalid username or password
|  | Username: "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
|  | Password: "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
|  | Lost Password |  | Help username find their password |  |  | Not yet | Need to finish
|  | Register |  | Users register account |  |  | Not yet | Need to finish
3. Validation of input in login | Input username and | Input |  | Login successful |  | 17/03/2017 | Worked as expected results | None
of teacher | password | Username: tungdt
Password: 12345
|  | Username: tungdt1 |  | Invalid username or password |  |  | Worked as expected results | None
Password: 12345
|  | Username: tungdt |  | Invalid username or password |  |  | Worked as expected results | None
Password: 123456
|  | Username: "blank" |  | Need to fill out this field |  |  | Worked as expected results | None
Password: 12345
|  | Username: tungdt |  | Need to fill out this field |  |  | Worked as expected results | None
Password: "blank"
|  | Username: "blank" |  | Need to fill out this field |  |  | Worked as expected results | None
Password: "blank"
|  | Lost Password |  | Help username find their password |  |  | Not yet | Need to finish
|  | Register |  | Users register account |  |  | Not yet | Need to finish
4. Validation of input in edit | Enter typical ,boundary | Input
profile as Teacher | values and value should | Phone "123456" |  | Edit profile successful |  |  | Worked as expected results | None
| be rejected | Address "HaNoi"
Email: "tungdt@gmail.com"
Password: "12345"
|  | Phone "blank" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
Address "HaNoi"
Email "mymail@gmail.com"
Password: "12345"
|  | Phone "12345678" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
Address "blank"
Email "mymail@gmail.com"
Password: "12345"
|  | Phone "12345678" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
Address "blank"
Email "blank"
Password: "12345"
|  | Phone "12345678" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
Address "HaNoi"
Email "myemail@gmail.com
Password: "blank"
|  | Phone "blank" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
Address "blank"
Email: "blank"
Password: "blank"
5.Validation of input | Enter typical ,boundary | Input String: |  |  |  | 16/03/2017
edit profile for edit profile | values and value should | Information "myhomeat.." |  | Input data successful |  |  | Worked as expected results | None
for Coordinator | be rejected | Email "huydd@gmail.com
ChangePasswordTo 12345
|  | Information "empty" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
|  | Email "huyddgmail.com" |  | Error message: Need signal @ in email adress
|  | ChangePassword "empty" |  | Error message: Need to fill out this field
|  | Information "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
|  | Email "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results
|  | ChangePassword "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
6. Validation of input in login | Input username and | Input |  |  |  | 16/03/2017
of Coordinator | password | UserName: coordinatorrrr |  | Login successfully |  |  | Worked as expected results | None
Password: 12345
Input
|  | UserName: coodinator |  |  |  |  | Worked as expected results | None
|  | Password: 12345 |  | Error message: Invalid username or password
Input
|  | UserName: lampt00512 |  |  |  |  | Worked as expected results | None
|  | Password: 1234 |  | Error message: Invalid username or password
|  | Username: "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
|  | Password: "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
|  | Lost Password |  | Help username find their password |  |  | Not yet | Need to finish
|  | Register |  | Users register account |  |  | Not yet | Need to finish
7.Validation of input | Enter typical ,boundary | Input String: |  |  |  | 16/03/2017
edit profile for edit profile | values and value should | Information "myhomeat.." |  | Input data successful |  |  | Worked as expected results | None
for Manager | be rejected | Email "huydd@gmail.com
ChangePasswordTo 12345
|  | Information "empty" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
|  | Email "huyddgmail.com" |  | Error message: Need signal @ in email adress
|  | ChangePassword "empty" |  | Error message: Need to fill out this field
|  | Information "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
|  | Email "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results
|  | ChangePassword "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
8. Validation of input in login | Input username and | Input |  |  |  | 16/03/2017
of Manager | password | UserName: manager |  | Login successfully |  |  | Worked as expected results | None
Password: 12345
Input
|  | UserName: managererere |  |  |  |  | Worked as expected results | None
|  | Password: 12345 |  | Error message: Invalid username or password
Input
|  | UserName: manager |  |  |  |  | Worked as expected results | None
|  | Password: 1234 |  | Error message: Invalid username or password
|  | Username: "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
|  | Password: "blank" |  | Error message: Need to fill out this fied |  |  | Worked as expected results | None
|  | Lost Password |  | Help username find their password |  |  | Not yet | Need to finish
|  | Register |  | Users register account |  |  | Not yet | Need to finish
9. Student send Claim | Click Upload Claim in Profile | Subject "blank" |  | Error message: Need to fill out this field |  | 2107-03-30 | Worked as expected results | None
|  | Body "blank" |  | Error message: Need to fill out this field |  |  | Worked as expected results | None
|  | Input Subject: !@#$%^&* |  | Error message: Do not enter these characters |  |  | Still running | Need to validate
|  | Input Body: A long text |  | Error message: Do not enter more than 500 characters |  |  | Still running | Need to validate
|  | Input Subject: Interaction Design |  | Upload successful |  |  | Worked as expected results | None
Input Body: Today I am sick so I would like
to take a break from studying this subject
|  | Input Subject: Enterprise Web Software |  | Upload successful |  |  | Worked as expected results | None
Development
Input Body: I have uploaded the CW to the
system but have not seen the status
uploaded successfully. Please review
|  | Upload evidence with claim with pdf file |  | Upload successful |  |  | Worked as expected results | None
|  | Upload evidence with claim with image file |  | Upload successful |  |  | Worked as expected results | None
| Click Upload Claim without Evident |  |  | Upload sucessful |  |  | Worked as expected results | None
10. Student upload evidence | Click Upload Claim | Upload evidence with pdf file no later than |  |  | Upload succesfful |  | Worked as expected results | None
3 days from the start date of Up load this claim
|  | Upload evidence with image file no later than |  |  | Upload successful |  | Worked as expected results | None
3 days from the start date of Up load this claim
|  | Upload evidence with pdf file later than |  |  | Button upload hidden |  | Worked as expected results | None
3 days
11. Take Feedback in Profile | Click upload Feedback |  |  | Show feedback page |  | 17/03/2017 | Worked as expected results | Need to finish
of Student
| Take feedback | Input text
|  | Input title: "blank" |  | Need to fill out this field |  |  | Worked as expected results | None
|  | Message "blank" |  | Need to fill out this field
Choose teacher: Doan Trung Tung
|  | Input title: "blank" |  | Need to fill out this field |  |  | Worked as expected results | None
|  | Message "sorrysir" |  | Can't sent without blank
Choose teacher: Doan Trung Tung
|  | Input title: "sorrysir" |  | Can't sent without blank |  |  | Worked as expected results | None
|  | Message "blank" |  | Need to fill out this field
Choose teacher: Doan Trung Tung
|  | Input title: "blank" |  | Need to fill out this field |  |  | Worked as expected results | None
|  | Message "blank" |  | Can't sent without blank
Choose teacher: Pham Van Vung
|  | Input title: "blank" |  | Need to fill out this field |  |  | Worked as expected results
|  | Message "sorrysir" |  | Can't sent without blank
Choose teacher: Pham Van Vung
|  | Input title: "sorrysir" |  | Need to fill out this field |  |  | Worked as expected results | None
|  | Message "blank" |  | Can't sent without blank
Choose teacher: Pham Van Vung
|  | Input title: "blank" |  | Need to fill out this field |  |  | Worked as expected results | None
|  | Message "blank" |  | Can't sent without blank
Choose teacher: Do Quoc Binh
|  | Input title: "blank" |  | Need to fill out this field |  |  | Worked as expected results | None
|  | Message "sorrysir" |  | Can't sent without blank
Choose teacher: Do Quoc Binh
|  | Input title: "sorry sir" |  | Need to fill out this field |  |  | Worked as expected results | None
|  | Message "blank" |  | Can't sent without blank
Choose teacher: Do Quoc Binh
12. Coordinator handling Claim | Take and answered Claim | Answered Subject Interaction Design |  | Resolve the claim for success |  |  | Worked as expected results | None
| Click View Claim in Profile | We will consider your claim |  | Send the answer letter to the email of the student sucessfully
Click in Action
|  | Answered Subject Enterprise Web Software |  | Resolve the claim for success |  |  | Worked as expected results | None
|  | Development |  | Send the answer to the email of the student successfully
We will fix your case as soon as possible
| Click View Claim in Profile | View your Claim list and the claims |  | Show all Claim |  |  | Worked as expected results | None
have status
| Take and answerd Claim | Rejected Claim |  | Resolve the claim for success
| Click View Claim in Profile | Answer letter: not accept |  | Send the answer letter to the email of the student successfully
Click in Reject
13. View Class as Student | Click to view Class in |  |  | Load Class pages anh display |  | 16/03/2017 | Worked as expected results | None
and Upload CourseWork | home page |  |  | classes list
| Choose subject in Course Categories |  |  | Show the subject and the class is |  |  | Not yet | Need to finish
| list |  |  | studying
View subject is studying
| Click to view document in class |  |  | Can view all the document in class |  |  | Woked as expected results | None
| Click to upload Coursework | [6 empty] | None
| Choose attach file | cw1pdf |  | Uploaded successful |  |  | Worked as expected results
|  | cw1.docx | cw1 .img | Error message: can not upload this type of file |  |  | Worked as expected results
| Click to download document in class | Document existed in Class | [5 empty] | None
| Link the document to download |  |  | Downloaded successful |  |  | Worked as expected results
15. View Class as Teacher | Click to view Class in |  |  | Load Class pages anh display |  | 17/03/2017 | Worked as expected results | None
and Upload document | home page |  |  | classes list
| Select upload in list: Slide | Name of file : Demo |  | Uploaded successful |  |  | Worked as expected results | None
Choose file: slide1.pdf
| Select upload in list: Slide | Name of file: meow |  | Uploaded successful |  |  | Worked as expected results | None
Choose file: mewo.img
| Select upload in list: Slide | Name of file: minutelogexample |  | Uploaded successful |  |  | Worked as expected results | None
Choose file: minutelogex.docx
| Select upload in list: Book | Name of file: Book for Study |  | Uploaded succeful |  |  | Worked as expected results
Choose file: BookBook.pdf
| Select upload in list: Book | Name of file: Book for Study |  | Uploaded succesful |  |  | Not yet | Need to code
Choose file: BookBook.docx
| Select upload in list: Book | Name of file: | Moew2 | Type file is wrong |  |  | Worked as expected results | None
Choose file: Meow2.pdf
| Select upload in list: Coursework Example | Name of file: CourseWork Example 1 |  | Uploaded successful |  |  | Worked as expected results | None
Choose file: cw1.pdf
| Select upload in list: Coursework Example | Name of file:CourseWork Example2 |  | Type file is wrong |  |  | Worked as expected results
Choose file: cw1.docx
| Select upload in list: Coursework Example | Name of file: | meow2 | Type file is wrong |  |  | Worked as expected results | None
Choose file: meow2.img
| Select upload in list: Test | Name of file: Test1 |  | Uploaded succesull |  |  | Worked as expected results | None
Choosefile: Test1.pdf
| Select upload in list: Test | Name of file: Test1 |  | Type file is wrong |  |  | Worked as expected results | None
Choose file: Test1.docx
| Select upload in list: Test | Name of file: meo |  | Type file is wrong |  |  | Worked as expected results | None
Choose file: meo.pdf
| Click to view Document |  |  | View fully document |  |  | Worked as expected results | None
| Click to download Document | Document existed in class |  | Downloaded succefull |  |  | Worked as expected results | None
in Study
| Click to download Document | Document existed in class |  | Downloaded succefull |  |  | Worked as expected results | None
in Book
| Click to download Document | Document existed in class |  | Downloaded succefull |  |  | Worked as expected results | None
in Coursework Example
| Click to download Document | Document existed in class |  | Downloaded succefull |  |  | Worked as expected results | None
in Test
16. Search | Input text in search tool | Input subject |  | Search successfull subject name |  | 16/03/2017 | Worked as expected results | None
| Input text in search tool | Input class |  | Search successfull class name |  |  | Worked as expected results | None
17. Coordinator tasks | Adding Student in class | Account Acc | "blank" | Error message: Need to fill out this field |  |  | Worked as expected results | None
|  | Acount Pass | "blank" | Error message: Need to fill out this field
|  | FullName | "blank" | Error message: Need to fill out this field
|  | Birthday | "blank" | Error message: Need to fill out this field
|  | Address | "blank" | Error message: Need to fill out this field
|  | Email | "blank" | Error message: Need to fill out this field
|  | Phone | "blank" | Error message: Need to fill out this field
|  | Postion | "blank" | Error message: Need to fill out this field
|  | Account Acc | "huydd" | Input data successful |  |  | Worked as expected results | None
|  | Acount Pass | "12345"
|  | Fullname | "Duc Huy"
|  | Birthday | "01/01/2017"
|  | Address | "Ha Noi"
|  | Email | "huydd@gmail.com"
|  | Phone | "12345"
|  | Postion | Student
Delete Student(Account by ID and position=1)
|  | Deleting some students existed |  | Deleted succefull |  |  | Worked as expected results | None
| Edit Student | Account Acc | "blank" | Error message: Need to fill out this field |  |  | Worked as expected results | None
|  | Acount Pass | "blank" | Error message: Need to fill out this field
|  | FullName | "blank" | Error message: Need to fill out this field
|  | Birthday | "blank" | Error message: Need to fill out this field
|  | Address | "blank" | Error message: Need to fill out this field
|  | Email | "blank" | Error message: Need to fill out this field
|  | Phone | "blank" | Error message: Need to fill out this field
|  | Postion | "blank" | Postion can not allow to change
|  | Account Acc | "huydd123" | Input data successful |  |  | Worked as expected results | None
|  | Acount Pass | "123456"
|  | Fullname | "Duc Huy Huy"
|  | Birthday | "02/02/2017
|  | Address | "London"
|  | Email | "huyddgc@gmail.com"
|  | Phone | "12345789"
|  | Postion | Student
| Adding Semester | Semester | "blank" | Error message: Need to fill out this field |  |  | Worked as expected results | None
|  | Semeter | "Semester1" | Input data successfull |  |  | Worked as expected results | None
|  | Semester | "adasdd@#@" | Error message: Can not enter special signal |  |  | Still running | Need validate
| Delete Semester (Semester by ID) | Deleting some semester existed |  | Deleted succefull |  |  | Worked as expected results | None
| Editing Semester | Semester | "blank" | Error message: Need to fill out this field |  |  | Worked as expected results | None
|  | Semeter | "Semester1.1" | Edit data successful |  |  | Worked as expected results | None
|  | Semester | "abcdsdd@#@" | Error message: Can not enter special signal |  |  | Worked as expected results | None
| Adding Subject | Name Subject | "blank" | Error message: Need to fill out this field |  |  | Worked as expected results | None
Choose Teacher: "Doan Thanh Tung"
Choose Class "TCH 1102"
|  | Name Subject | "CMS Project" | Input data successfully |  |  | Worked as expected results | None
Choose Teacher: "Doan Thanh Tung"
Choose Class "TCH 1102"
|  | Name Subject | "CMS @asbcd" | Error message: Can not enter special signal |  |  | Still running | Need validate
Choose Teacher: "Doan Thanh Tung"
Choose Class "TCH 1102"
| Delete Subject (Subject by ID) | Deleting some Subject existed |  | Deleted succefull |  |  | Worked as expected results | None
| Editing Subject | Name Subject | "blank" | Error message: Need to fill out this field |  |  | Worked as expected results | None
Choose Teacher: "Doan Thanh Tung"
Choose Class "TCH 1102"
|  | Name Subject | "CMS Big Project" | Input data successfully |  |  | Worked as expected results | None
Choose Teacher: "Doan Thanh Tung"
Choose Class "TCH 1102"
|  | Name Subject | "CMS sadsa@#@" | Error message: Can not enter special signal |  |  | Worked as expected results | None
Choose Teacher: "Doan Thanh Tung"
Choose Class "TCH 1102"
18. Manager can view | Click on view chart |  |  | Show view successfully |  |  | Worked as expected results | None
| Click on view static |  |  | Show view successfully |  |  | Worked as expected results | None
| Click on view Claims |  |  | Show view successfully |  |  | Worked as expected results | None